This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
Select any team name you prefer.
Please enter your name as it appears in Blackboard.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product_Backlog
Product Name:	Enigma Machine
Team ID:

	Team Member Name					Initials	Student ID
Required

Sprint #	Remaining	Completed This Sprint			Comment
0	20			Total	Total number of features (in column H)
1	18	2		1	Total features left at the end of Sprint #1
2	16	2		2	Total features left at the end of Sprint #2
3	15	1		3	...and so on
4	15	0

				Sprints
Feature ID	Priority	Required	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
CF	1	1	13		Finished in Sprint 2	User	Use Enigma encryption to encrypt a message	verify that the encryption process works
CC	2	1	5		Finished in Sprint 3	User	Use Enigma to Decrypt a message	Verify that decryption works
GUI	3	1	8		Finished in Sprint 1	User	Have a help section on how to use the encryption	Lower mistakes
PS	4	1	5	1	Finished in Sprint 1	User	Have a history blurb about its usage and impact	Show the importance of this encryption technology
IGUI	5	2	13		In Work	User	add Change Cogs function	Change the cogs in the machine	There were five cogs for the machine, and they could be set to different numbers each
BB	7	2	3		In Work	User	generate cog and plugboard settings in a text file	Complete the machine to its historical accuracy
CB	6	2	2		In Work	User	make the plugboard (before the CoPlug file)	Increase permutations
CO	8	2	8		Finished in Sprint 2	User	save Message to a variable/ temp variable	make it easy to handle message data
POC	9	2	3		In Work	User	enable saving messages to a text file	make it easier to check previous messages
CSB	10	3	8		In Work	User	enable loading messages to a text file	make it easier to check previous messages
CE	11	3	13			User	make save files with (message+CoPlug file)	change the save file to something more modular
MST	12	3	5			User	make load files with (message+CoPlug file)	change the load file to something more modular
SAVD	13	3	8			User	make sure the files read correctly	verify save data and the load files
LOAD	14	4	5		In Work	User	make a main menu for the machine	Make it easier to interact with the machine
POS	15	4	5			User	enable dialogs for encrption entry	Make encription more intuitive
PIX	16	4	21			User	enable dialogs for decrption entry	Make decryption more intuitive
CM	17	4	3			User	make dialogs for the rest of the menu options	Menu options are easier to interact with
P&L	18	4	8			User	make the plug board easier to interact with through buttons	Make the plugboard more obvious to understand
RI	19		5			User	Have the message be diplayed encrypted while the user is typing it	Show the process taking place
RTM	20	4	8			User	Have the message be displayed decrypted while the user is typing it.	Show the process taking place
Product Backlog Burn Chart
Features Remaining at end of Sprint
Sprints

## Sprint_01_Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 30		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 06
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	4
Day 1 Left	4	0
Day 2 Left	4	0
Day 3 Left	4	0
Day 4 Left	4	0
Day 5 Left	4	0
Day 6 Left	4	0
Day 7 Left	3	1

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			make view, and machine to encrypt
2			make plug board to add more to encryption
3			Have menu and extra text blurbs finished
4			lay the groundwork for the cogs function	Completed Day 7
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_02_Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Nov 06		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 13
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_03_Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Nov 13		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 20
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	4
Day 1 Left	4	0
Day 2 Left	4	0
Day 3 Left	4	0
Day 4 Left	2	2
Day 5 Left	2	0
Day 6 Left	2	0
Day 7 Left	1	1

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint	Completed Day 4
2			Finish the complex encryption Algorithm	Completed Day 4
3			Write the menu	Completed Day 7
4			Finish writing the basic menu
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_04_Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Nov 20		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 27
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	4
Day 1 Left	4	0
Day 2 Left	4	0
Day 3 Left	4	0
Day 4 Left	4	0
Day 5 Left	4	0
Day 6 Left	4	0
Day 7 Left	4	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2			Make plugboard
3			Upgrade menu
4			Get the File I/O working
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days